## Sheet1
PROJECT X - AUTOMATED ATTENDANCE SYSTEM
TASK ID | TASK NAME | SUB TASK ID | DELIVIRABLES | ESTIMATED HOURS | ASSIGNEE | START DATE | END DATE | STATUS
1 | Project Setup | 1.1 | Create project repository, assign team roles, and set up tools | 3 | Christopher Burgos | 2025-02-27 | 2025-02-27 | DONE
|  | 1.2 | Define project scope and objectives | 3 | Joomer Jake Caballero | 2025-02-28 | 2025-02-28 | DONE
2 | Requirements Documentation | 2.1 | Document system requirements (R1-R8) | 5 | Joomer Jake Caballero | 02/29/25 | 02/29/25 | DONE
|  | 2.2 | Validate requirements with stakeholders | 4 | Leopoldo Dumadangon IV | 02/30/25 | 02/30/25 | DONE
3 | System Architecture Design | 3.1 | Create high-level system architecture diagram | 6 | Leopoldo Dumadangon IV | 02/31/25 | 02/31/25 | DONE
|  | 3.2 | Document technology stack (frontend, backend, database) | 8 | Christopher Burgos | 2025-03-01 | 2025-03-01 | DONE
4 | Use Case Development | 4.1 | Develop use case diagrams and scenarios (Mark Attendance, Generate Reports) | 5 | Christopher Burgos | 2025-03-02 | 2025-03-02 | DONE
|  | 4.2 | Document alternate flows and exceptions for use cases | 4 | Joomer Jake Caballero | 2025-03-03 | 2025-03-03 | DONE
5 | Conceptual Diagram | 5.1 | Create UML class diagram for system components | 6 | Joomer Jake Caballero | 2025-03-04 | 2025-03-04 | DONE
|  | 5.2 | Document relationships between classes | 3 | Leopoldo Dumadangon IV | 2025-03-05 | 2025-03-05 | DONE
6 | User Role & Access Control Design | 6.1 | Document user roles and access control design (R1.1-R1.4) | 5 | Leopoldo Dumadangon IV | 2025-03-06 | 2025-03-06 | DONE
|  | 6.2 | Define role-based permissions and workflows | 6 | Christopher Burgos | 2025-03-07 | 2025-03-07 | DONE
7 | Attendance Recording Design | 7.1 | Document attendance recording process (R2.1-R2.4) | 7 | Christopher Burgos | 2025-03-08 | 2025-03-08 | DONE
|  | 7.2 | Design offline mode functionality for attendance recording | 8 | Joomer Jake Caballero | 2025-03-09 | 2025-03-09 | ONGOING
8 | Device Registration Design | 8.1 | Document device registration and tracking design (R3.1-R3.3) | 4 | Joomer Jake Caballero | 2025-03-10 | 2025-03-10 | DONE
|  | 8.2 | Design GPS tracking integration for registered devices | 3 | Leopoldo Dumadangon IV | 2025-03-11 | 2025-03-11 | PENDING
9 | Student Enrollment Design | 9.1 | Document student enrollment and management design (R4.1-R4.3) | 4 | Leopoldo Dumadangon IV | 2025-03-11 | 2025-03-11 | DONE
|  | 9.2 | Design student profile picture capture and storage process | 5 | Christopher Burgos | 2025-03-11 | 2025-03-11 | ONGOING
10 | Reporting & Data Access Design | 10.1 | Document reporting and data access design (R5.1.1-R5.1.3) | 6 | Christopher Burgos | 2025-03-11 | 2025-03-11 | DONE
|  | 10.2 | Design export functionality for reports (PDF, CSV) | 7 | Joomer Jake Caballero | 2025-03-11 | 2025-03-11 | PENDING
11 | Photo Capture & Storage Design | 11.1 | Document photo capture and storage design (R6.1-R6.3) | 8 | Joomer Jake Caballero | 2025-03-12 | 2025-03-12 | DONE
|  | 11.2 | Design secure access controls for stored images | 9 | Leopoldo Dumadangon IV | 2025-03-12 | 2025-03-12 | PENDING
12 | Testing Criteria Documentation | 12.1 | Document testing criteria (Unit Testing, System Testing, UAT) (R8.1-R8.3) | 4 | Leopoldo Dumadangon IV | 2025-03-12 | 2025-03-12 | DONE
|  | 12.2 | Define test cases for each module | 5 | Christopher Burgos | 2025-03-12 | 2025-03-12 | DONE
13 | Final Manuscript Compilation | 13.1 | Compile all sections into a final manuscript (Word/PDF format) | 6 | Christopher Burgos | 2025-03-14 | 2025-03-14 | DONE
|  | 13.2 | Format and structure the manuscript for readability | 7 | Joomer Jake Caballero | 2025-03-14 | 2025-03-14 | DONE
14 | Review & Final Edits | 14.1 | Review manuscript for accuracy and completeness | 1 | Joomer Jake Caballero | 2025-03-14 | 2025-03-14 | DONE
|  | 14.2 | Incorporate feedback from stakeholders | 2 | Leopoldo Dumadangon IV | 2025-03-15 | 2025-03-15 | ONGOING
15 | Project Closure | 15.1 | Finalize and submit manuscript | 1 | Leopoldo Dumadangon IV | 2025-03-15 | 2025-03-15 | ONGOING